## bugs
Bug List
# | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
1 | 2024-02-16 | Shirley Qi | P3 | Resolved | Shirley | Sometimes active enemy will jitter if the player and enemy are on the same x coordinate (different y coordinate, meaning they are on different platforms) | Enemies should walk and stop smoothly | Enemies occasionally jitter until player starts moving again | Try to stay above or below the enemy and stop moving
2 | 2024-02-16 | Kelsey Chua | P3 | Resolved | Kelsey | Passive enemy sometimes gets stuck on the boundary, and jitters | Enemy should smoothly bounce off its edges | Enemy occasionally gets stuck, jitters, then frees itself | Unsure - Enemy has its own movement, so you must wait for it to get stuck
3 | 2024-02-16 | Kelsey Chua | P3 | Resolved | Kelsey | Player starts bouncing without any up keys/action | Player should stay on the platform unless the up arrow or "w" is clicked | Sometimes during gameplay: Player bounces up and down without key action, sometimes at death: player bounces up and down after contact with the enemy | During gameplay: Unsure - there has not been a pattern. At death: contact with the enemy while/after pressing the up key
4 | 2024-03-04 | Kelsey Chua | P3 | Resolved | Unassigned | Enemies do not spawn upon game initialization | All entities should appear upon initialization | Enemies do not spawn upon game initialization | Start the game
5 | 2024-03-04 | Johnny Lau | P4 | Resolved | Unassigned | Moving the window of the game will cause all entities to shift locations | All entities should stick to their positions | Entities will disappear when moving the game window | Move the game window
6 | 2024-03-04 | Kelsey Chua | P3 | Resolved | Johnny | Player unable to move left at times | Player should have smooth movement left, right, up | Player sometimes gets stuck in place when moving left | Move around a little, stop, then try moving left. This will occasionally reproduce
7 | 2024-03-04 | Karen Shao | P5 NONCRITICAL(visual only, no effect on gameplay) | Open | Unassigned | black lines will flicker around images when moving | level and background should stay the same | black lines appear above grass and other areas upon movement | move around and jump, especially near grass
8 | 2024-03-04 | Shirley Qi | P5 | Resolved | Shirley | Sometimes player will still be in the falling sprite image rather than resetting to the standing sprite image when landing on the ground | Player should reset to standing sprite | When landing on some platforms, player will stay in falling sprite | Try to jump and land on different platforms to see if the sprite resets to standing
9 | 2024-03-11 | Andy Zhao | P4 | Resolved | Shirley, Andy, Karen | Player clipping out from draw order | Player should be in front of background elements | Player gets rendered behind background after restarting or transitioning levels | Transition or restart a level. This will occasionally reproduce
10 | 2024-03-13 | Andy Zhao | P3 | Resolved | Andy | Player falls through one-way platforms (and normal platforms) | Player should stay on top of one way platforms | Player clips through the platform | Find a one way platform with a solid wall next to it (in an L shape). Jump and hold the direction key to move into the wall. As you fall, you will clip through the platform
11 | 2024-03-25 | Christopher Lew | P4 | Resolved | Christopher | certain sound effects not playing | Sound effect should play when performing certain actions | No sound plays | Picking up apples sound effect not working
12 | 2024-03-25 | Christopher Lew | P4 | Resolved | Christopher | sound effects play when in dialogue state | sound effects should be disabled during dialogue | footsteps play during dialogue | get into dialogue with sister
13 | 2024-03-25 | Christopher Lew | P4 NONCRITICAL (can get unstuck by jumping/moving) | Open | Unassigned | Player gets stuck on the hill platforms | player should smoothly continue walking left or right | player gets stuck when starting to climb a hill platform (can get out of it by jumping) | walk right or left from a square platform to a hill platform without jumping
14 | 2024-03-24 | Christopher Lew | P4 NONCRITICAL (can get unstuck by jumping/moving) | Open | Unassigned | Player gets stuck on square platform when approaching at a 45 degree angle from a jump | player's y velocity should not get stuck and either start to fall or pass through the playtform | player gets stuck after jumping and approaching a sqaure platform at 45 degrees (can get out of it by jumping) | turn on debug mode then jump at a square platform in the air from a 45 degree angle, easy to do in sewers
15 | 2024-03-29 | Christopher lew | P3 | Resolved | Christopher | Player can spam attack sfx | sfx should only play when the attack animation plays | sfx gets played whenever player presses z key | press z
16 | 2024-04-02 | Christopher lew | P3 | Resolved | Christopher | Battle music continues after death | Music should change back to non-combat music on respawn | Battle music continues after death | die while in battle

## bug_severities
Severity | Description
P0 | crash bug; game crashes and is unrecoverable
P1 | game stopping bug, but no crash; cannot keep playing
P2 | serious, game not working as expected
P3 | annoying, could ship but loss of marks
P4 | annoying or limiting, but could be shipped as-is
P5 | minor or feature that nice to have but could ship in future release